Example logical framework matrix for Sanitation Programme

|  | Intervention Logic | Objectively Verifiable Indicators | Sources of Verification | Risks and Assumptions |
| --- | --- | --- | --- | --- |
| Principal Objective (IMPACT) | Contribute to the improvement of the health and well being of 20,000 people in Region R (Country C) within four months | Mortality and morbidity data within accepted limits (see WHO) No major outbreaks of communicable diseases in the target area | Un & Government reports Other agency reports Health facility data Community consultation e.g. pocket voting, FGD |  |
| Specific Objective (OUTCOME) | X,000 households have the material, informational and motivational means to carry out appropriate hygiene and sanitation practices within four months. | Areas within 30 m radius of all dwelling and water points free from observable excreta within four months. 70% of the target population using sanitary latrines within three months. 60% of the target population washing hands with soap / alternatives after defaecation within four months 50% of the target population can list one change that they have made as a result of attending an interactive hygiene promotion session At least 80% of households dispose of solid waste safely At least 80% of pregnant women and children are sleeping under LLINs The project target area is free from solid waste and stagnant water | Exploratory walks reports Focus group discussions Information from other NGOs. Surveys Community monitoring tools | Conflict in the neighbouring country does not spill over the border and destabilise the country. WFP and National Red Cross continue to provide sufficient food rations and non food items. Sufficient water is provided by other ERUs /agencies |
| Results R1 (outputs) | - X no of men, women and children have access to safe sanitary facilities within four months. | 70% of facilities constructed by the end of three months 1 latrine is constructed per 20-50 people after community consultation The majority (over two-thirds) of women and men, in FGDs express satisfaction with the safety, privacy and accessibility of latrines | Engineers monitoring and output records. Focus Group discussions Household visits Questionnaire survey | IDPs remain in the camp |
| Results R2 (OUPUTS) | - X no of men, women and children are enabled to practice safer hygiene in a dignified and culturally appropriate manner within four months | 75% of latrines are clean on spot inspections after 3 months and 90% after four months At least 80% of latrines have hand washing facilities that are in use after four months (observation of people using/evidence of water in tank and on ground) Each household reports the presence of soap on random weekly visits All women and girls have access to appropriate sanitary materials and underwear At least 80% of trained hygiene promoters are holding at least two meetings/10 household visits per week within 4 months 70% of target population can list three key ways to prevent diarrhoea by end of campaign (At least 70% of caretakers can demonstrate how to make up and give ORS/SSS correctly) | Latrine monitoring forms. Observation Weekly random transect walk Focus group discussions with women and girls held monthly with two groups of 12 people Random household Visits Hand washing demonstrations with children Questionnaire surveys, and interviews. | Regular distribution of soap continues |
| Results R3 (OUPUTS) | All sections of the community are aware of what they can do to prevent vector borne disease and take action to control these diseases within four months | At least 70% of families with children under five know how to prevent malaria and manage fever. | Health centre records, focus group discussions, pocket charts, observation | Assumes accessibility of health facilities Available and timely supply of nets Available and timely supply of registered chemicals |
| Activities R1 (INPUTS) | Activities associated with R1 A1. Establish a coordination system among the hygiene promotion team, stakeholders and ERU / RDRT / NIT teams. A2. Discuss with stakeholders the design of the latrine and hand washing facilities. A3. Train a set of local artisans and RC volunteers in latrine, hand washing facilities construction and vector control techniques. A4. Construction of community latrines and hand washing facilities. A5. Development of latrine (and water point) management system with users group during construction period. A6. Identify and train communal latrine attendants during construction period. | Means Material resources Building materials Cleaning materials Potties Human resources Engineers Public health promoters Community promoters Trained attendants | Costs Sanitation equipment Hygiene kits Promotional material Promotional activities Transport costs International staff Local staff Capital expenditure | Adequate supply of materials is maintained Adequate labour force is identified Suitably qualified personnel can be identified |
| Activities R2 (INPUTS) | Activities associated with R2 PHASE 1: Implement a rapid hygiene promotion campaign and distribution of hygiene kits. A1. Identify and train hygiene promotion coordinators and supervisors of community facilitators. A2. Identify and train at least 1 community facilitator per 1,000 population in hygiene promotion. A3. Carry out a 2 week Hygiene campaign on priority hygiene issues using standard channels of communication and IEC materials. A4. Distribute hygiene kits. PHASE 2: Implement a more participatory hygiene promotion campaign in the second and third month. A1. Complete baseline (social marketing) research by the end of 6 weeks with key stakeholders A2. Design materials adapted to the target population, pre-test and print IEC materials by the end of the second month. A3. Identify and select the most effective communication channels A4. Continue participatory hygiene promotion activities (responding where necessary to disease outbreaks) | Material resources Sanitation equipment Promotional materials Transport Hygiene materials Sanitary materials for women Cleaning materials Bins Transport Human resources Engineers – international and national Hygiene Promoters/volunteers international and national Interpreters for international staff |  |  |
| Activities R3 (INPUTS) | Activities associated with R3 A1. Organize community meetings A2. Distribute tools to community groups A3. Distribute LLINs A4. Carry out promotional activities A5. Carry out spraying activities Common activities to all results. A1. Monitoring & Evaluation system initiated within one month and refinement of system during the following weeks. A2. Good practice sharing and lessons learnt dissemination processes at the end of the third month. |  |  |  |

Acceptable and useful changes will need to be defined/rated

Safely will need to be defined according to chosen disposal system

These would be worked out with the community at the same time as establishment of community indicators. Some tools could be pocket voting, tally sheets (with pictures if literacy is low) or ranking

Satisfaction will need to be defined in terms of safety, privacy, dignity, accessibility, suitability, adequacy and other community defined indicators.

Appropriate will need to be defined – have consultations taken place, are women happy with what is provided

If doing Child-to-Child or other activities, the indicator needs to state what is expected of the promoter over a given period