Example logical framework matrix (following the ECHO format)

|  | Intervention Logic | Objectively Verifiable Indicators | Sources of Verification | Risks and Assumptions |
| --- | --- | --- | --- | --- |
| Principal Objective (IMPACT) | To contribute to the reduction of preventable, communicable diseases and to restore coping mechanisms of affected population | People are no longer dependent on emergency relief Mortality and morbidity data within accepted limits (see WHO) No major outbreaks of communicable diseases in target area X% reduction in communicable diseases as perceived by community members after x months | Un & Government reports Other agency reports Health facility data Community consultation e.g. pocket voting, FGD |  |
| Specific Objective (OUTCOME) | Men, women and children in the target population (x no) have increased access to, and make optimal use of, water and sanitation facilities, and take action to protect themselves against threats to public health | X no of people continuously have access to potable water after x months X no of people can demonstrate improved hygiene practices after x months More than 80% of men, women and children are using and maintaining latrines after x months At least 80% of latrines have hand washing facilities that are in use after x months At least 80% of households dispose of solid waste safely The majority (over two-thirds) of women in FGDs express satisfaction with the safety, privacy and accessibility of latrines, bathing facilities and laundry slabs At least 70% of caretakers can demonstrate how to make up and give ORS/SSS correctly | Information from other NGOs. Focus group discussions. Surveys Community monitoring tools | Conflict in the neighbouring country does not spill over the border and destabilise the host country. The health centres set up by the other INGO remain operational. UNHCR continue to provide sufficient food rations, shelter, and blankets. |
| Results (OUPUTS) | - X no of men, women and children have access to safe sanitary facilities within six months. - X no of men, women and children have access to safe drinking water according to Sphere standards within x months _________________________ - X no of men, women and children are enabled to practice safer hygiene in a dignified and culturally appropriate manner | 1 latrine constructed per 20 people after community consultation No faecal matter observed in the target area ________________________ At least 80% of target group accesses at least 15 litres water/day per person. Maximum distance from shelter/home to water points is 500m. Water meets international quality standards (Sphere) Queuing time at water sources no more than 15 minutes ________________________ At least 80% of trained PHP’s are holding at least two meetings/10 household visits per week Hand washing facilities are provided at all latrines and a system is in place to replenish them Each household reports the presence of soap on random weekly visits On weekly observation at water points at least 80% of jerry cans meet the criteria of a clean jerry can All women and girls have access to appropriate sanitary materials and underwear At least 80% households dig and use garbage pit The project target area is free from solid waste and stagnant water | Latrine monitoring forms. Reports by latrine assistants. Observation Weekly random transect walk Focus group discussions with women and girls held monthly with two groups of 12 people __________________________ Engineers monitoring and output records. Records from water point attendants. Weekly water testing records Surveys __________________________ Observation. Random household Visits Reports from latrine attendants and water point attendants. Hand washing demonstrations with children Focus group discussions, surveys, and interviews. Weekly random transect walks | Government border guards are able to improve security to reduce/prevent rebel raids. Refugees stay in the camp. |
| Activities (INPUTS) | Result 1 – Adequate sanitary facilities in the camp - Set up temporary defecation areas. - 400 gender-segregated latrines constructed in line with international standards. - 100 hand-washing facilities constructed and being refilled daily - 50 latrine attendants trained and equipped. - Construction of 200 gender-segregated bathing facilities. - Construction of 80 community-washing facilities (laundry). - Consultation with female and male refugees to identify design and suitable sites for sanitation facilities. - Provision of potties for under-five - Monitoring system established _________________________ Result 2 – Adequate clean water - Trucking of water (first phase only) - Installation of six bladders - Installation of 32 water points in the refugee camp. - Training of 32 water point attendants in camp. - Construction of 20 hand pumps in local village. - Training of 20 hand pump attendants in village. - Establishment of a stock of community spares for water pumps in village. - Establishment of water management committee in local village - Monitoring system established _________________________ Result 3 – Improved hygiene practices in camp - Training of 16 community hygiene promoters in camp - House-to-house visits, community meetings, water point meetings carried out - Child-to-Child activities carried out - Provision of 4000 water containers. - Provision of 200 community hygiene packs. - Provision of 2000 household hygiene packs every month for six months (soap, disinfectant, laundry soap, etc, for one family for one month). - Provision of sanitary towels and underwear to women - Production of hygiene promotion materials - Solid waste management plan in place - Provision of bins - Provision of cleaning materials - Clean up campaigns - Monitoring system established | Means Material resources Building materials Cleaning materials Potties Human resources Engineers Public health promoters Community promoters Trained attendants Material resources WatSan equipment Spare parts Promotional materials Oxfam Delagua testing kit Transport Human resources Engineers – international and national Public health promoters – international and national Interpreter for international staff Water pump attendants Volunteers Material resources Hygiene materials Water containers Sanitary materials for women Cleaning materials Bins Promotional materials Community theatre Puppet shows Child-to-Child activities Transport Human resources Public health promoters – both international and national Volunteers Interpreter for international staff | Costs WatSan equipment Hygiene kits Promotional material Promotional activities Transport costs International staff Local staff Capital expenditure | Construction materials remain available in adequate amounts. |
|  |  |  |  | Preconditions National government gives NGO registration to work in the country. |

### Resources

1. Websites

- www.dfid.gov.uk/FOI/tools

- http://europa.eu.int/comm/echo/pdf_files/partnership/pcm_echo_en.pdf

These will need to be specified e.g. hand washing at critical times (after defecation and before eating), safe excreta disposal, safe water storage

Safely will need to be defined according to chosen disposal system

Satisfaction will need to be defined in terms of safety, privacy, dignity, accessibility, suitability, adequacy and other community defined indicators.

These would be worked out with the community at the same time as establishment of community indicators. Some tools could be pocket voting, tally sheets (with pictures if literacy is low) or ranking

If doing Child-to-Child or other activities, the indicator needs to state what is expected of the promoter over a given period

A definition of clean: no visible dirt, no cracks, lid intact