PROJECT MONITORING PLAN

| WHO | WHAT | HOW/WITH WHOM | FORMAT | HOW OFTEN |
| --- | --- | --- | --- | --- |
| Project Manager | Overall Humanitarian Situation Overall responsibility to ensure M and E carried out Staff performance Donor reporting | Agency/Government Meetings Team Leaders Collation of Information from team and observation/discussions during field visits | Minutes from meetings Performance Appraisal Narrative Report | Weekly Yearly Six monthly Monthly |
| Watsan Team Leader | Overall water & sanitation status/strategies Staff performance Collation of data from engineers & hygiene promoters Field visits | Co-ordination meetings Engineers & Hygiene Promoters Observation/Discussions with community members and staff | Minutes Performance Appraisals Project monitoring form Monthly reports | Weekly Yearly Weekly/monthly Weekly |
| Engineers | Construction outputs and quality of work Water Quantity & Quality, Functioning systems, design suitability | Field observations Delaqua kit Discussions with users Team Meetings | Project Records Monthly Reports Water Qualiity testing forms | Weekly Daily One off testing for faecal coliforms and other chemical tests if possible As necessary Weekly |
| Hygiene Promoters | Use and maintenance of facilities, hand washing, use of ORS, user satisfaction(safety, privacy etc.), participation, training of facilitators and committees, Other promotional activities, protection issues/incidents, health status | Mini surveys Focus Group discussions with men, women and children Pocket charts, demonstrations, observation, Clinic records and discussions with clinic staff Team Meetings | Survey Monitoring Forms HP Action Plans Monitoring Reporting Form | Weekly/ Monthly 19 households |
| Community Volunteers | Use and maintenance of facilities, community hygiene actions and risks | Discussions, household visits Observation Meetings with Hygiene Promoters and Engineers | Verbal reports, Pictoral Latrine monitoring form | Weekly Monthly 10 households |
| Community Members | Community Defined Indicators | Observation, discussion | Verbal reports | As time allows |
| Monitoring and Evaluation Officer | Project Indicators and processes Training on M and E | Facilitation of use of above methods and feedback to community Training evaluation | Project Report Evaluation Forms | Monthly |