## Slide 1: Urban WASH Technical Working Group Nairobi, September 2017 One Stop Shop Case Studies.
Federation WASH
WHERE WE WORK
National Society(s) active in this Project: Danish Red Cross, Uganda Red Cross (until 2015). External partners: A2I, EnviClean & DMS Africa, Ålborg University and Copenhagen business school.
Country/Location of Project: Uganda, Kasese municipality: Kinsaga market and communities in 12 Wards.
Title of Project/Case Study: One Stop Shop Project.
Time scale of project: Initial assessments and feasibility studies were carried out in 2012 and 2013. Implementation of Red Cross Hygiene Promotion activities 01.04.2014-30.06.2016
Approximate Total Budget (USD): One Stop Shop building (go’n see tour, design/establishment of building, running cost & monitoring): 167.000 USD
Health clinic and HP campaigns: 109.925 USD

## Slide 2: Urban WASH Technical Working Group Nairobi, September 2017 One Stop Shop Case Studies.
Federation WASH
WHERE WE WORK
Target population:
7.591Children and adolescents (age 6-18) through education (PHASE)
2.572 Adults in the targeted community through PHAST (24 promotors, 300 PHAST members, 1500 community members) & PHASE (20 trained teachers, 157 teachers, 571 families).
15.022 indirect beneficiaries reached with PHASE and PHAST
Through radio og talk show, health messages are likely to have been conveyed to the entire district (approx. 750.000 people)

## Slide 3: Urban WASH Technical Working Group Nairobi, September 2017 Standard PP for Case Studies.
Federation WASH
Describe what the project delivers in water supply: Selling of water, establishment of hand washing facilities in households and schools.
Describe what the project delivers in sanitation: Improved sanitation in the form of shared sanitation; a communal privately run facility selling toilet visits and showers, sanitary products, water and mobile charging. It has been reported by the municipality that open defecation has decreased at the market place.
Describe what the project delivers in Hygiene: Community awareness raising through PHASE/PHAST groups on safe water chains, improved sanitation and hygiene practice. Dissemination of health messages through radio and talk shows
Describe capacity building of target population: Community groups were trained to disseminate messages on hygiene to communities and motivated Village Health Teams monitoring hygiene at household level. The PHASE approach used in schools raised children’s awareness on hygiene.
Describe capacity building of WASH service providers: The local team working at the OSS facility were trained in costumer handling, hygiene and cleaning, economy and accounting.

## Slide 4: Urban WASH Technical Working Group Nairobi, September 2017 Standard PP for Case Studies.
Federation WASH
Describe Achievements and lessons learned, what worked well?
  Importance of realistic ambitions and the right partners on board
  Partner continuity and trust/personal engagement are important
  Partners should have resources available (funding/HR)
  Firm political commitments from local authorities is key
  Important to understand local context and engaging service users (user experience is a must and design matters)
  Technically the OSS facility and maternal clinic have worked without any breakdowns for 3 and 2 years.
  Community awareness raising have reached most of the community and it was reported that the number of diarrhoea cases decreased.
  The OSS pilot project has given partners proof of concept.

## Slide 5: Urban WASH Technical Working Group Nairobi, September 2017 Standard PP for Case Studies.
Federation WASH
Describe challenges, what did not go so well?
  The interrupted partnership with URCS happened at a critical moment and created some challenges for the local project manager.
  Working within a complex partnership with multiple different partners requires a lot more time and resources for coordination and information sharing
What resources did you need or lack?
Non-earmarked funding
Skills and knowledge in how to create sustainable business models/market research/business development

## Slide 6: Additional remarks
Recommendations
Follow up on the health services in order to capture progress, challenges and lessons learnt. As DRC is no longer present in Uganda, it is recommended that a review is carried out through an external consultancy.
Follow up with the municipality health department on retrieving their health statistics in order to assess, if the reported declining rate of diarrhea cases by health officers holds true. This finding would further support and inform the partners on the impact and sustainability of the OSS business case.
In future agreements with the private sector, DRC should mention and/or include a clause highlighting the possibility of delays when engaging with RC/RC.
Follow-up with the local authorities to ensure that the allocation for water and cleaning of the health clinic is included in the municipality budget.
Action plan and mutual agreement to ensure proper transfer of ownership of the buildings and continued access to services for the citizens and the customers.
Emphasis should be placed on drafting exit strategies, even though it can be difficult to envision in an inception period of an innovative pilot project. There is a potential reputational risk for RC if the exit is not carried out properly.
Federation WASH